## Sheet1
Risk | Risk Resolution Measures | Justification
Real Time Performance Shortfalls | Project Manager that keeps developers on task. | Keeps the project on schedule
Unrealistic Schedules and Budgets | Leave enough time to adjust schedule if needed. | Helps to reach project goals
Developing the wrong User Interface | Research what users will be using the interface. | Helps create the right project
Gold-Plating | Research users and make sure interface isn't overdone. | Helps create the perfect user interface
Developing the wrong functions and properties | Continued testing as project moves along to ensure its correct. | Helps to create successful project